## Slide 1
FJ Barbosa Electronics
15 February 2011
Estimated Hardware Availability for FDC Tests
Production Schedule Summary
Preamp 50 Nov 2011
628 Feb 2012 – July 2012
fADC125 50 May 2012
      143 Oct 2012 - Feb 2013
Single Board Test Station Aug 2011
Multiple Board Test Station Jan 2012
F1TDC 20 Oct 2012
        72 Nov 2012 - Apr 2013
Single Board Test Station Jan 2012
Multiple Board Test Station Oct 2012
NOTE: Single & Multiple Board Test Stations must be available by indicated dates for production testing.

## Slide 2
FJ Barbosa Electronics
15 February 2011
Test Plan
Single-Board Test
(Module Specific)
Protocol Level 1: Chip Scope, USB ROC, PC Based
Incoming Inspection
Label, Database Entry
Ship to JLab
Diagnostics
Re-work
Multiple Board Test
Burn-in
Full VME readout
Protocol Level 2: ROC, CODA, Linux
Ship to JLab
Diagnostics
Re-work
Database Entry
Package & Store
Fail
Fail
@ JLab
@ JLab