## Counter Info
Scintillator Counter # | Why it was removed from TAGH | Problems Found | What was repaired | Date Taken Out | Date Reinstalled
83 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
84 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
92 | Loose scintillator | Scintillator no longer securely attached to light guide, scintillator bent | scintillator replaced, plastic endpiece added | 2019-07-10 | 2019-07-17
98 | Loose scintillator | Scintillator no longer securely attached to light guide |  | 2019-07-17
101 | Loose scintillator | Scintillator no longer securely attached to light guide |  | 2019-07-17
110 | Loose scintillator | Scintillator no longer securely attached to light guide |  | 2019-07-17
113 | Loose scintillator | Scintillator broken in two towards base | scintillator replaced, plastic endpiece added | 2019-06-10 | 2019-07-02
116 | Loose scintillator | Scintillator broken in two towards base, 1 disconnected wire at the circuit board | scintillator replaced, wire reattached, plastic endpiece added | 2019-06-10 | 2019-07-02
119 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-02 | 2019-07-10
123 | Loose scintillator | Scintillator no longer securely attached to light guide, large air bubble between light-guide and PMT | scintillator reattached, light-guide and PMT were replaced with one without a bubble | 2019-07-10 | 2019-07-17
125 | Loose scintillator | Scintillator no longer securely attached to light guide, 1 disconnected wire at the circuit board | scintillator reattached, wire reattached, plastic endpiece added | 2019-06-10 | 2019-07-02
126 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
138 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
144 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-06-10 | 2019-07-02
161 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-06-10 | 2019-07-02
170 | Loose scintillator | Scintillator no longer securely attached to light guide |  | 2019-07-17
184 | Loose scintillator | Scintillator no longer securely attached to light guide, 1 disconnected wire at the circuit board, amplifier and divider not proper distance apart (was an 1/8th an inch apart) | scintillator reattached, plastic endpiece added, wire reconnected | 2019-07-10 | 2019-07-17
187 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-02 | 2019-07-10
196 | Loose scintillator | Scintillator no longer securely attached to light guide, scratches on scintillator around base | scintillator replaced, plastic endpiece added | 2019-07-02 | 2019-07-10
212 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-02 | 2019-07-10
228 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-02 | 2019-07-10
229 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
230 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added | 2019-07-10 | 2019-07-17
231 | Loose scintillator | Scintillator no longer securely attached to light guide |  | 2019-07-17